## Sheet1
TASK NAME | NAME | DURATION | START | FINISH
SPRINT 1
Identify key stakeholders | Swathish | 2 days | 2022-06-18 | 2022-06-20
Form project team | Swathish | 2 days | 2022-06-21 | 2022-06-23
Create backlog | Ashish | 2 days | 2022-06-24 | 2022-06-26
Cost estimation | Soju | 2 days | 2022-06-28 | 2022-06-30
SPRINT 2
Create project timeline | Ashish | 1 day | 2022-07-02 | 2022-07-04
Planning | Helan | 3 days | 2022-07-06 | 2022-07-09
Execution | Swathish | 2 days | 2022-07-10 | 2022-07-12
Demo | Ashish, Soju | 3 days | 2022-07-12 | 2022-07-15
Implementation | Helan | 6 days | 2022-07-10 | 2022-07-14
SPRINT 3
Final implementation | Helan | 5 days | 2021-07-23 | 2021-07-27
28 days